## Sheet1
|  | Meeting Minutes 2 | Date
2016-01-07
Project Name |  | Train Management System
Participants |  | Mr.ChienBD, HuyNQ, DatNT, LinhTT, DaoDD, TungDD,
Remarks |  | Team TMS
The work was done |  | Remarks | Implementers | Completion Date
| 1 | Unified requirement for the project | All of member
| 2 | Unified support tools for project | All of member
Resource management : Github
Database : MySQL ¦ Programming language: PHP
| 3 | Find out about UML and sketches of use case | TungDD, DaoDD, DatNT
| 4 | Find out about System Sequence Diagram | HuyNQ, LinhTT
| 5 | Learn about the same technology already exists | All of member
| 6 | Set up templates for Weekly report | TungDD
7
8
The work wasn't done |  | Remarks | Why? | Completion Date
| 1 | Unfinished the use case | improper request of teacher | 2016-09-01
2
3
4
5
Issue |  | Remarks | solution issue | Completion Date
| 7 | Customers do not cooperate | don't take the money and talk this is a demo for the project
| 8 | The group members are not near each other | focus on one spot
9
10
Prepared by |  | TungDD
Designation
Email Address |  | tungddse02761@fpt.edu.vn